## Engagements
Engagement Code | Engagement Name | Client | Service Line | Engagement Lead | Quarter | Date Started | Planned End Date | Planned Hours | Actual Hours | Planned Fees (AUD) | Actual Fees (AUD) | Budget Variance % | Margin % | Status | Comments
ENG-1001 | ANZ — Customer Experience Review | ANZ | Audit & Assurance | sarah chen | Q3 FY26 |  | 17/03/2026 | 300 | 279 | 225000 | 185600 | -17.5 | 2.3 | On Track | Project delayed by client decision on vendor selection.
ENG-1002 | Commonwealth Bank — Digital Transformation | Commonwealth Bank | Strategy & Transactions | Priya Patel | Q2 FY26 | 2025-10-18 | 2026-12-19 | 300 | 296 | 225000 | 236100 | 4.9 | 18 | Completed | Risks: key client SME on extended leave; backup contact engaged.
ENG-1003 | Transurban — Workforce Planning | Transurban | Audit & Assurance | DAVID THOMPSON | Q1 FY26 | 23-Jul-2025 | 03-Oct-2025 | 800 | 877 | 360000 | 396000 | 10 | -0.4 | Completed | Risks: key client SME on extended leave; backup contact engaged.
ENG-1004 | Telstra — Cost Optimisation | Telstra | Strategy & Transactions | david thompson | Q2 FY26 | 16-12-2025 | 03-05-2026 | 300 | 433 | 225000 | 372700 | 65.6 | 29.8 | Completed | Burn rate above plan due to weekend work on regulatory deadline.
ENG-1005 | Transurban — SAP Implementation | Transurban | Strategy & Transactions | Priya Patel | Q2 FY26 | 07/10/2025 | 05/02/2026 | 1200 | 1628 | 900000 | 1139600 | 26.6 | -1.7 | On Track | Scope creep flagged — partner to discuss with client lead.
ENG-1006 | CSL — Customer Experience Review | CSL | Tax | james o'brien | Q1 FY26 |  | 22/10/2025 | 400 | 261 | 240000 | 161700 | -32.6 | -3 | On Track | Resource constraints on senior manager bench — escalated to People team.
ENG-1007 | Wesfarmers — Customer Experience Review | Wesfarmers | Tax | Aisha Khan | Q1 FY26 |  | 02/01/2025 | 400 | 564 | 180000 | 215700 | 19.8 | -9.9 | On Track | Steering committee delayed by 2 weeks; final report timing at risk.
ENG-1008 | Wesfarmers — M&A Due Diligence | Wesfarmers | Consulting | linh nguyen | Q3 FY26 | 16 Feb 2026 | 04 Apr 2026 | 1200 | 1265 | 720000 | 754100 | 4.7 | 23.8 | At Risk
ENG-1009 | ANZ — Operating Model Redesign | ANZ | Audit & Assurance | LINH NGUYEN | Q1 FY26 | 2025-09-28 | 2025-01-17 | 500 | 489 | 262500 | 265400 | 1.1 | 28.3 | At Risk | Client added new stakeholder; re-running interview round.
ENG-1010 | Commonwealth Bank — ESG Reporting | Commonwealth Bank | Tax | robert mckenzie | Q3 FY26 | 2026-01-01 | 2026-05-16 | 800 | 878 | 480000 | 460500 | -4.1 | -3.3 | Delayed | Margin compression due to additional travel and onshore senior hours.
ENG-1011 | Westpac — Data & Analytics Strategy | Westpac | Tax | david thompson | Q1 FY26 | 04/09/2025 | 26/02/2025 | 800 | 1224 | 540000 | 817000 | 51.3 | -12.8 | At Risk | Client requested scope expansion — pending change request approval.
ENG-1012 | Transurban — M&A Due Diligence | Transurban | Consulting | ROBERT MCKENZIE | Q2 FY26 | 18-10-2025 | 01-01-2026 | 300 | 299 | 157500 | 172300 | 9.4 | 1.7 | Delayed
ENG-1013 | Macquarie — Supply Chain Review | Macquarie | Consulting | aisha khan | Q1 FY26 | 12-Sep-2025 | 22-Feb-2025 | 1500 | 1879 | 1125000 | 1205700 | 7.2 | 12.2 | On Track | Data access issues with client IT — slowing diagnostic workstream.
ENG-1014 | ANZ — Data & Analytics Strategy | ANZ | Consulting | michael wong | Q2 FY26 | 17-12-2025 | 26-05-2026 | 500 | 505 | 375000 | 325100 | -13.3 | -10.4 | On Track
ENG-1015 | AGL — Workforce Planning | AGL | Consulting | ROBERT MCKENZIE | Q1 FY26 | 17/09/2025 | 18/01/2025 | 300 | 312 | 202500 | 183600 | -9.3 | 22.8 | At Risk | Burn rate above plan due to weekend work on regulatory deadline.
ENG-1016 | AGL — M&A Due Diligence | AGL | Consulting | Robert McKenzie | Q3 FY26 | 13/01/2026 | 06/06/2026 | 1500 | 1476 | 675000 | 708400 | 4.9 | -7.1 | Completed | Client requested scope expansion — pending change request approval.
ENG-1017 | Macquarie — Cyber Maturity Assessment | Macquarie | Tax | michael wong | Q1 FY26 | 03-07-2025 | 09-11-2025 | 400 | 416 | 240000 | 242500 | 1 | 16.7 | Completed | Audit findings being remediated; expect re-test in two weeks.
ENG-1018 | AGL — Digital Transformation | AGL | Strategy & Transactions | PRIYA PATEL | Q1 FY26 | 2025-08-01 | 2025-10-26 | 300 | 276 | 225000 | 201800 | -10.3 | 34.1 | On Track
ENG-1019 | Qantas — Cloud Migration | Qantas | Consulting | Linh Nguyen | Q1 FY26 | 10/07/2025 | 17/11/2025 | 400 | 439 | 180000 | 168800 | -6.2 | 25.7 | At Risk
ENG-1020 | Commonwealth Bank — Workforce Planning | Commonwealth Bank | Tax | Michael Wong | Q3 FY26 | 2026-02-18 | 2026-07-17 | 800 | 840 | 420000 | 428300 | 2 | -13.2 | On Track | Scope creep flagged — partner to discuss with client lead.
ENG-1021 | Woolworths — Digital Transformation | Woolworths | Tax | Michael Wong | Q3 FY26 |  | 2026-06-23 | 600 | 655 | 450000 | 465200 | 3.4 | -6.4 | At Risk | Burn rate above plan due to weekend work on regulatory deadline.
ENG-1022 | Westpac — Cost Optimisation | Westpac | Consulting | aisha khan | Q2 FY26 | 17-Nov-2025 | 08-Feb-2026 | 300 | 421 | 202500 | 243400 | 20.2 | 6 | On Track
ENG-1023 | Wesfarmers — Cost Optimisation | Wesfarmers | Consulting | Robert McKenzie | Q2 FY26 | 20-Dec-2025 | 02-Mar-2026 | 1500 | 2074 | 1125000 | 1587400 | 41.1 | -5.4 | At Risk | Steering committee delayed by 2 weeks; final report timing at risk.
ENG-1024 | BHP — M&A Due Diligence | BHP | Strategy & Transactions | David Thompson | Q2 FY26 | 18-11-2025 | 21-01-2026 | 1200 | 1119 | 900000 | 939400 | 4.4 | -3.8 | Completed | Scope creep flagged — partner to discuss with client lead.
ENG-1025 | AGL — Financial Audit FY26 | AGL | Strategy & Transactions | james o'brien | Q3 FY26 | 15 Mar 2026 | 28 Aug 2026 | 600 | 621 | 270000 | 287800 | 6.6 | 7.3 | Delayed | Data access issues with client IT — slowing diagnostic workstream.
ENG-1026 | Suncorp — Digital Transformation | Suncorp | Strategy & Transactions | robert mckenzie | Q3 FY26 | 23 Jan 2026 | 22 Apr 2026 | 1200 | 1318 | 900000 | 899300 | -0.1 | 37 | On Track | Quality review complete. Minor edits before partner sign-off.
ENG-1027 | Telstra — Workforce Planning | Telstra | Tax | linh nguyen | Q1 FY26 | 03-Jul-2025 | 05-Sep-2025 | 2000 | 2159 | 1200000 | 1191000 | -0.8 | 33.3 | On Track | On track. No issues raised this fortnight.
ENG-1028 | Suncorp — Workforce Planning | Suncorp | Strategy & Transactions | Aisha Khan | Q3 FY26 | 2026-01-14 | 2026-05-13 | 800 | 753 | 420000 | 420500 | 0.1 | 33.5 | Delayed | Steering committee delayed by 2 weeks; final report timing at risk.
ENG-1029 | Wesfarmers — Tax Restructure | Wesfarmers | Tax | DAVID THOMPSON | Q2 FY26 | 2025-10-09 | 2026-12-02 | 600 | 635 | 405000 | 478000 | 18 | 29.4 | On Track | Margin compression due to additional travel and onshore senior hours.
ENG-1030 | BHP — Regulatory Compliance Uplift | BHP | Strategy & Transactions | ROBERT MCKENZIE | Q1 FY26 | 28-09-2025 | 16-01-2025 | 400 | 389 | 240000 | 226800 | -5.5 | 3 | Completed | Client signed off on Phase 1; Phase 2 kickoff next week.
ENG-1031 | Woolworths — Tax Restructure | Woolworths | Consulting | JAMES O'BRIEN | Q2 FY26 | 08 Dec 2025 | 11 May 2026 | 500 | 659 | 225000 | 280400 | 24.6 | 8.9 | At Risk | Client requested scope expansion — pending change request approval.
ENG-1032 | Wesfarmers — Regulatory Compliance Uplift | Wesfarmers | Tax | James O'Brien | Q2 FY26 | 2025-11-25 | 2026-01-16 | 1500 | 1609 | 675000 | 674300 | -0.1 | 3.4 | Completed | Risks: key client SME on extended leave; backup contact engaged.
ENG-1033 | Westpac — M&A Due Diligence | Westpac | Audit & Assurance | Sarah Chen | Q3 FY26 | 19-02-2026 | 01-07-2026 | 1500 | 1447 | 675000 | 597100 | -11.5 | -1 | On Track | Final deliverable submitted. Awaiting client commercial sign-off.
ENG-1034 | BHP — Operating Model Redesign | BHP | Strategy & Transactions | priya patel | Q3 FY26 | 2026-01-21 | 2026-05-05 | 300 | 391 | 225000 | 266100 | 18.3 | 4 | On Track | Client requested scope expansion — pending change request approval.
ENG-1035 | Coles — Workforce Planning | Coles | Risk Advisory | linh nguyen | Q3 FY26 |  | 18/04/2026 | 600 | 760 | 405000 | 448500 | 10.7 | 2.5 | Delayed | Client added new stakeholder; re-running interview round.
ENG-1036 | BHP — Cost Optimisation | BHP | Tax | Aisha Khan | Q3 FY26 | 2026-02-07 | 2026-04-26 | 500 | 528 | 262500 | 254800 | -2.9 | 2.2 | Delayed | Client signed off on Phase 1; Phase 2 kickoff next week.
ENG-1037 | Suncorp — Cloud Migration | Suncorp | Risk Advisory | James O'Brien | Q2 FY26 | 02-12-2025 | 13-03-2026 | 400 | 381 | 270000 | 287800 | 6.6 | 32.6 | On Track | On track. No issues raised this fortnight.
ENG-1038 | Rio Tinto — Cloud Migration | Rio Tinto | Audit & Assurance | Robert McKenzie | Q2 FY26 | 2025-12-24 | 2026-05-27 | 300 | 389 | 180000 | 227800 | 26.6 | 32.7 | At Risk | Project delayed by client decision on vendor selection.
ENG-1039 | Coles — Regulatory Compliance Uplift | Coles | Audit & Assurance | michael wong | Q3 FY26 | 07 Feb 2026 | 18 Jun 2026 | 1200 | 1612 | 810000 | 938100 | 15.8 | -2.1 | Delayed | Margin compression due to additional travel and onshore senior hours.
ENG-1040 | Macquarie — SAP Implementation | Macquarie | Strategy & Transactions | linh nguyen | Q3 FY26 |  | 2026-05-09 | 300 | 384 | 202500 | 275900 | 36.2 | 13.4 | Delayed | Risks: key client SME on extended leave; backup contact engaged.
ENG-1041 | ANZ — Data & Analytics Strategy | ANZ | Tax | Priya Patel | Q3 FY26 | 27/02/2026 | 20/05/2026 | 800 | 809 | 540000 | 587500 | 8.8 | -14.5 | On Track | Audit findings being remediated; expect re-test in two weeks.
ENG-1042 | Origin Energy — Risk & Controls Review | Origin Energy | Consulting | MICHAEL WONG | Q3 FY26 | 07 Jan 2026 | 14 Mar 2026 | 400 | 412 | 210000 | 232300 | 10.6 | 31 | On Track | Quality review complete. Minor edits before partner sign-off.

## Engagement Leads
Engagement Code | Engagement Lead (Canonical) | Email | Office | Grade
ENG-1001 | Sarah Chen | sarah.chen@deloitte.com.au | Brisbane | Senior Manager
ENG-1002 | Priya Patel | priya.patel@deloitte.com.au | Brisbane | Senior Manager
ENG-1003 | David Thompson | david.thompson@deloitte.com.au | Melbourne | Director
ENG-1004 | David Thompson | david.thompson@deloitte.com.au | Melbourne | Director
ENG-1005 | Priya Patel | priya.patel@deloitte.com.au | Brisbane | Senior Manager
ENG-1006 | James O'Brien | james.obrien@deloitte.com.au | Brisbane | Director
ENG-1007 | Aisha Khan | aisha.khan@deloitte.com.au | Melbourne | Director
ENG-1008 | Linh Nguyen | linh.nguyen@deloitte.com.au | Perth | Director
ENG-1009 | Linh Nguyen | linh.nguyen@deloitte.com.au | Perth | Director
ENG-1010 | Robert McKenzie | robert.mckenzie@deloitte.com.au | Brisbane | Director
ENG-1011 | David Thompson | david.thompson@deloitte.com.au | Melbourne | Director
ENG-1012 | Robert McKenzie | robert.mckenzie@deloitte.com.au | Brisbane | Director
ENG-1013 | Aisha Khan | aisha.khan@deloitte.com.au | Melbourne | Director
ENG-1014 | Michael Wong | michael.wong@deloitte.com.au | Canberra | Senior Manager
ENG-1015 | Robert McKenzie | robert.mckenzie@deloitte.com.au | Brisbane | Director
ENG-1016 | Robert McKenzie | robert.mckenzie@deloitte.com.au | Brisbane | Director
ENG-1017 | Michael Wong | michael.wong@deloitte.com.au | Canberra | Senior Manager
ENG-1018 | Priya Patel | priya.patel@deloitte.com.au | Brisbane | Senior Manager
ENG-1019 | Linh Nguyen | linh.nguyen@deloitte.com.au | Perth | Director
ENG-1020 | Michael Wong | michael.wong@deloitte.com.au | Canberra | Senior Manager
ENG-1021 | Michael Wong | michael.wong@deloitte.com.au | Canberra | Senior Manager
ENG-1022 | Aisha Khan | aisha.khan@deloitte.com.au | Melbourne | Director
ENG-1023 | Robert McKenzie | robert.mckenzie@deloitte.com.au | Brisbane | Director
ENG-1024 | David Thompson | david.thompson@deloitte.com.au | Melbourne | Director
ENG-1025 | James O'Brien | james.obrien@deloitte.com.au | Brisbane | Director
ENG-1026 | Robert McKenzie | robert.mckenzie@deloitte.com.au | Brisbane | Director
ENG-1027 | Linh Nguyen | linh.nguyen@deloitte.com.au | Perth | Director
ENG-1028 | Aisha Khan | aisha.khan@deloitte.com.au | Melbourne | Director
ENG-1029 | David Thompson | david.thompson@deloitte.com.au | Melbourne | Director
ENG-1030 | Robert McKenzie | robert.mckenzie@deloitte.com.au | Brisbane | Director
ENG-1031 | James O'Brien | james.obrien@deloitte.com.au | Brisbane | Director
ENG-1032 | James O'Brien | james.obrien@deloitte.com.au | Brisbane | Director
ENG-1033 | Sarah Chen | sarah.chen@deloitte.com.au | Brisbane | Senior Manager
ENG-1034 | Priya Patel | priya.patel@deloitte.com.au | Brisbane | Senior Manager
ENG-1035 | Linh Nguyen | linh.nguyen@deloitte.com.au | Perth | Director
ENG-1036 | Aisha Khan | aisha.khan@deloitte.com.au | Melbourne | Director
ENG-1037 | James O'Brien | james.obrien@deloitte.com.au | Brisbane | Director
ENG-1038 | Robert McKenzie | robert.mckenzie@deloitte.com.au | Brisbane | Director
ENG-1039 | Michael Wong | michael.wong@deloitte.com.au | Canberra | Senior Manager
ENG-1040 | Linh Nguyen | linh.nguyen@deloitte.com.au | Perth | Director
ENG-1041 | Priya Patel | priya.patel@deloitte.com.au | Brisbane | Senior Manager
ENG-1042 | Michael Wong | michael.wong@deloitte.com.au | Canberra | Senior Manager

## October Add-On
INSTRUCTIONS FOR FACILITATOR:
Copy rows 4-13 below (without the header) and paste them at the bottom of the Engagements sheet during the live-update demo.
Engagement Code | Engagement Name | Client | Service Line | Engagement Lead | Quarter | Date Started | Planned End Date | Planned Hours | Actual Hours | Planned Fees (AUD) | Actual Fees (AUD) | Budget Variance % | Margin % | Status | Comments
ENG-1043 | Telstra — Customer Experience Review | Telstra | Audit & Assurance | Linh Nguyen | Q2 FY26 | 08-Oct-2026 | 21-Nov-2026 | 300 | 423 | 157500 | 214300 | 36.1 | -5.4 | At Risk | Margin under pressure — onshore senior hours higher than plan.
ENG-1044 | CSL — Digital Transformation | CSL | Tax | Linh Nguyen | Q2 FY26 | 08-Oct-2026 | 02-Nov-2026 | 400 | 560 | 240000 | 366000 | 52.5 | -6.8 | At Risk | Margin under pressure — onshore senior hours higher than plan.
ENG-1045 | AGL — Operating Model Redesign | AGL | Tax | Michael Wong | Q2 FY26 | 21-Oct-2026 | 07-Dec-2026 | 300 | 402 | 180000 | 230700 | 28.2 | 2 | At Risk | New engagement kicked off in October.
ENG-1046 | Rio Tinto — Operating Model Redesign | Rio Tinto | Risk Advisory | David Thompson | Q2 FY26 | 14-Oct-2026 | 06-Dec-2026 | 1200 | 1203 | 720000 | 689100 | -4.3 | 19.9 | On Track | Client added scope post-kickoff — change request in flight.
ENG-1047 | Origin Energy — Risk & Controls Review | Origin Energy | Strategy & Transactions | Aisha Khan | Q2 FY26 | 22-Oct-2026 | 21-Nov-2026 | 1200 | 1158 | 720000 | 701500 | -2.6 | 14.5 | On Track | Strong start; partner pleased with diagnostic outputs.
ENG-1048 | Origin Energy — Digital Transformation | Origin Energy | Audit & Assurance | Linh Nguyen | Q2 FY26 | 24-Oct-2026 | 14-Dec-2026 | 800 | 762 | 540000 | 538300 | -0.3 | 17.4 | On Track | Client added scope post-kickoff — change request in flight.
ENG-1049 | Westpac — Regulatory Compliance Uplift | Westpac | Consulting | Priya Patel | Q2 FY26 | 14-Oct-2026 | 27-Nov-2026 | 300 | 305 | 202500 | 209800 | 3.6 | 11.9 | On Track | New engagement kicked off in October.
ENG-1050 | ANZ — Customer Experience Review | ANZ | Strategy & Transactions | Michael Wong | Q2 FY26 | 19-Oct-2026 | 24-Dec-2026 | 1200 | 1175 | 810000 | 787100 | -2.8 | 20.5 | On Track | New engagement kicked off in October.
ENG-1051 | Wesfarmers — Data & Analytics Strategy | Wesfarmers | Strategy & Transactions | James O'Brien | Q2 FY26 | 10-Oct-2026 | 27-Nov-2026 | 300 | 334 | 225000 | 249700 | 11 | 22.6 | On Track | Client added scope post-kickoff — change request in flight.
ENG-1052 | Woolworths — Financial Audit FY26 | Woolworths | Strategy & Transactions | Aisha Khan | Q2 FY26 | 20-Oct-2026 | 27-Nov-2026 | 800 | 784 | 480000 | 449800 | -6.3 | 30.5 | On Track | Margin under pressure — onshore senior hours higher than plan.