## Read me
DCE Copilot Training — Demo dataset (fictional)
Purpose: practice file for Copilot in Excel and the Analyst agent.
All clients, engagement leads, and figures are fictional and for training only.
The 'Engagements' sheet is a Central Europe advisory engagement portfolio.
Calculated columns (Margin %, Budget Variance %, Realisation %, Hours Variance %) use formulas.
Standard blended rate assumption is on the Engagements sheet (cell R1/S1).
Note: a few rows contain deliberately inconsistent formatting (mixed case, a missing
end date) so you can demonstrate data clean-up. Several engagements are intentional
outliers (high budget variance, negative margin, hours well over plan).

## Engagements
Engagement Code | Client | Service Line | Engagement Lead | Region | Start Date | Original End Date | Status | Planned Hours | Actual Hours | Fees (EUR 000) | Budget Cost (EUR 000) | Actual Cost (EUR 000) | Margin % | Budget Variance % | Hours Variance % | Realisation % | Status Note | Std blended rate (EUR/h) | 185
CE-2026-1001 | Project Quartz | Risk Advisory | Lukas Weber | Vienna | 2026-01-12 | 2026-05-24 | On track | 1720 | 1883 | 337.3 | 226 | 228.3 | 32.32% | 1.018% | 9.477% | 96.83% | Resourcing gap flagged for next month.
CE-2026-1002 | Project Cobalt | Financial Advisory | Sofia Horvath | Prague | 2026-01-13 | 2026-05-26 | At risk | 1760 | 1584 | 348.4 | 236.9 | 241.6 | 30.65% | 1.984% | -10% | 118.9% | Change request pending approval.
CE-2026-1003 | Project Delta | Audit & Assurance | Tomas Varga | Zurich | 2026-01-14 | 2026-05-28 | On track | 1800 | 2169 | 359.6 | 248.1 | 255.5 | 28.95% | 2.983% | 20.5% | 89.62% | Delivered ahead of plan; reference call agreed.
CE-2026-1004 | Project Falcon | Tax & Legal | Elena Popescu | Bratislava | 2026-01-15 | 2026-05-30 | Delivered | 1840 | 1858 | 371 | 259.7 | 270.1 | 27.2% | 4.005% | 0.9783% | 107.9% | Budget pressure from extra review cycles.
CE-2026-1005 | Project Granite | Consulting | JAKUB NOWAK | Bucharest | 2026-01-16 | 2026-06-01 | On track | 1880 | 2472 | 382.6 | 271.6 | 285.2 | 25.46% | 5.007% | 31.49% | 83.66% | Key milestone met; partner readout next week.
CE-2026-1006 | Project Harbor | Risk Advisory | Klara Schmidt | Budapest | 2026-01-17 | 2026-06-03 | At risk | 1920 | 2150 | 394.3 | 283.9 | 300.9 | 23.69% | 5.988% | 11.98% | 99.13% | Dependency on client IT release.
CE-2026-1007 | Project Indigo | Financial Advisory | Andrei Ionescu | Warsaw | 2026-01-18 | 2026-06-05 | Delivered | 1960 | 1813 | 406.1 | 296.5 | 317.3 | 21.87% | 7.015% | -7.5% | 121.1% | Scope stable; on plan.
CE-2026-1008 | Project Juniper | Audit & Assurance | Maja Kovacevic | Ljubljana | 2026-01-19 | 2026-06-07 | at risk | 2000 | 2460 | 418.1 | 309.4 | 334.2 | 20.07% | 8.016% | 23% | 91.87%
CE-2026-1009 | Project Kestrel | Tax & Legal | Filip Urban | Zagreb | 2026-01-20 | 2026-06-09 | On track | 2040 | 2111 | 430.2 | 322.6 | 351.6 | 18.27% | 8.989% | 3.48% | 110.2% | Escalated to lead partner.
CE-2026-1010 | Project Larch | Consulting | Anna Kovac | Vienna | 2026-01-21 | 2026-06-11 | At risk | 2080 | 2787 | 327.1 | 248.6 | 273.5 | 16.39% | 10.02% | 33.99% | 63.44% | Client raised scope concerns on workstream 2.
CE-2026-1011 | Project Maple | Risk Advisory | Marek Dvorak | Prague | 2026-01-22 | 2026-06-13 | On track | 2120 | 2427 | 337.3 | 259.7 | 288.3 | 14.53% | 11.01% | 14.48% | 75.12% | Awaiting client data; timeline slipping.
CE-2026-1012 | Project Atlas | Financial Advisory | petra novak | Zurich | 2026-01-23 | 2026-06-15 | Delivered | 2160 | 2052 | 347.7 | 215.6 | 241.5 | 30.54% | 12.01% | -5% | 91.59% | Strong client feedback at steering committee.
CE-2026-1013 | Project Helix | Audit & Assurance | Lukas Weber | Bratislava | 2026-01-24 | 2026-06-17 | On track | 2200 | 2760 | 358.2 | 225.7 | 255 | 28.81% | 12.98% | 25.45% | 70.15% | Resourcing gap flagged for next month.
CE-2026-1014 | Project Meridian | Tax & Legal | Sofia Horvath | Bucharest | 2026-01-25 | 2026-06-19 | At risk | 2240 | 2374 | 368.8 | 236 | 269 | 27.06% | 13.98% | 5.982% | 83.97% | Change request pending approval.
CE-2026-1015 | Project Vega | Consulting | Tomas Varga | Budapest | 2026-01-26 | 2026-06-21 | Delivered | 2280 | 3112 | 379.6 | 246.7 | 283.7 | 25.26% | 15% | 36.49% | 65.93% | Delivered ahead of plan; reference call agreed.
CE-2026-1016 | Project Orion | Risk Advisory | Elena Popescu | Warsaw | 2026-01-27 | 2026-06-23 | On hold | 2320 | 2714 | 390.6 | 257.8 | 299 | 23.45% | 15.98% | 16.98% | 77.79% | Budget pressure from extra review cycles.
CE-2026-1017 | Project Lyra | Financial Advisory | Jakub Nowak | Ljubljana | 2026-01-28 | 2026-06-25 | On track | 2360 | 2301 | 401.7 | 269.1 | 314.8 | 21.63% | 16.98% | -2.5% | 94.37% | Key milestone met; partner readout next week.
CE-2026-1018 | Project Nova | Audit & Assurance | Klara Schmidt | Zagreb | 2026-01-29 | 2026-06-27 | At risk | 2400 | 3072 | 412.9 | 280.8 | 331.3 | 19.76% | 17.98% | 28% | 72.65% | Dependency on client IT release.
CE-2026-1019 | Project Aurora | Tax & Legal | Andrei Ionescu | Vienna | 2026-01-30 | 2026-06-29 | On track | 2440 | 2647 | 424.3 | 292.8 | 348.4 | 17.89% | 18.99% | 8.484% | 86.65% | Scope stable; on plan.
CE-2026-1020 | Project Pulsar | Consulting | Maja Kovacevic | Prague | 2026-01-31 |  | Delivered | 2480 | 3447 | 435.9 | 305.1 | 366.1 | 16.01% | 19.99% | 38.99% | 68.36%
CE-2026-1021 | Project Quartz | Risk Advisory | Filip Urban | Zurich | 2026-02-01 | 2026-07-03 | On track | 2520 | 3011 | 447.6 | 317.8 | 384.5 | 14.1% | 20.99% | 19.48% | 80.35% | Escalated to lead partner.
CE-2026-1022 | Project Cobalt | Financial Advisory | Anna Kovac | Bratislava | 2026-02-02 | 2026-07-05 | At risk | 2560 | 2560 | 459.4 | 330.8 | 403.6 | 12.15% | 22.01% | 0% | 97% | Client raised scope concerns on workstream 2.
CE-2026-1023 | Project Delta | Audit & Assurance | Marek Dvorak | Bucharest | 2026-02-03 | 2026-07-07 | Delivered | 2600 | 3393 | 471.4 | 344.1 | 423.2 | 10.22% | 22.99% | 30.5% | 75.1% | Awaiting client data; timeline slipping.
CE-2026-1024 | Project Falcon | Tax & Legal | Petra Novak | Budapest | 2026-02-04 | 2026-07-09 | On hold | 2640 | 2930 | 483.5 | 357.8 | 443.7 | 8.232% | 24.01% | 10.98% | 89.2% | Strong client feedback at steering committee.
CE-2026-1025 | Project Granite | Consulting | Lukas Weber | Warsaw | 2026-02-05 | 2026-07-11 | On track | 2680 | 2452 | 495.8 | 371.9 | 464.9 | 6.232% | 25.01% | -8.507% | 109.3% | Resourcing gap flagged for next month.
CE-2026-1026 | Project Harbor | Risk Advisory | Sofia Horvath | Ljubljana | 2026-02-06 | 2026-07-13 | At risk | 2720 | 3318 | 508.2 | 386.2 | 486.6 | 4.25% | 26% | 21.99% | 82.79% | Change request pending approval.
CE-2026-1027 | Project Indigo | Financial Advisory | Tomas Varga | Zagreb | 2026-02-07 | 2026-07-15 | On track | 2760 | 2828 | 520.8 | 401 | 614.5 | -17.99% | 53.24% | 2.464% | 99.55% | Delivered ahead of plan; reference call agreed.
CE-2026-1028 | Project Juniper | Audit & Assurance | Elena Popescu | Vienna | 2026-02-08 | 2026-07-17 | Delivered | 400 | 532 | 76.2 | 47.2 | 60.4 | 20.73% | 27.97% | 33% | 77.42% | Budget pressure from extra review cycles.
CE-2026-1029 | Project Kestrel | Tax & Legal | Jakub Nowak | Prague | 2026-02-09 | 2026-07-19 | On track | 440 | 499 | 84.7 | 53.4 | 68.9 | 18.65% | 29.03% | 13.41% | 91.75% | Key milestone met; partner readout next week.
CE-2026-1030 | Project Larch | Consulting | Klara Schmidt | Zurich | 2026-02-10 | 2026-07-21 | At risk | 480 | 451 | 93.2 | 59.6 | 77.5 | 16.85% | 30.03% | -6.042% | 111.7% | Dependency on client IT release.
CE-2026-1031 | Project Maple | Risk Advisory | Andrei Ionescu | Bratislava | 2026-02-11 | 2026-07-23 | Delivered | 520 | 647 | 102 | 66.3 | 86.9 | 14.8% | 31.07% | 24.42% | 85.22% | Scope stable; on plan.
CE-2026-1032 | Project Atlas | Financial Advisory | Maja Kovacevic | Bucharest | 2026-02-12 | 2026-07-25 | On hold | 560 | 588 | 110.9 | 73.2 | 67.3 | 39.31% | -8.06% | 5% | 101.9%
CE-2026-1033 | Project Helix | Audit & Assurance | Filip Urban | Budapest | 2026-02-13 | 2026-07-27 | On track | 600 | 813 | 119.9 | 80.3 | 74.7 | 37.7% | -6.974% | 35.5% | 79.72% | Escalated to lead partner.
CE-2026-1034 | Project Meridian | Tax & Legal | Anna Kovac | Warsaw | 2026-02-14 | 2026-03-31 | At risk | 640 | 992 | 129.1 | 87.8 | 82.5 | 36.1% | -6.036% | 55% | 70.35% | Client raised scope concerns on workstream 2.
CE-2026-1035 | Project Vega | Consulting | Marek Dvorak | Ljubljana | 2026-02-15 | 2026-04-02 | On track | 680 | 656 | 138.4 | 95.5 | 90.7 | 34.47% | -5.026% | -3.529% | 114% | Awaiting client data; timeline slipping.
CE-2026-1036 | Project Orion | Risk Advisory | Petra Novak | Zagreb | 2026-02-16 | 2026-04-04 | Delivered | 720 | 914 | 147.9 | 103.5 | 99.4 | 32.79% | -3.961% | 26.94% | 87.47% | Strong client feedback at steering committee.
CE-2026-1037 | Project Lyra | Financial Advisory | Lukas Weber | Vienna | 2026-02-17 | 2026-04-06 | On track | 760 | 817 | 157.5 | 111.8 | 108.4 | 31.17% | -3.041% | 7.5% | 104.2% | Resourcing gap flagged for next month.
CE-2026-1038 | Project Nova | Audit & Assurance | Sofia Horvath | Prague | 2026-02-18 | 2026-04-08 | At risk | 800 | 1104 | 167.2 | 120.4 | 118 | 29.43% | -1.993% | 38% | 81.86% | Change request pending approval.
CE-2026-1039 | Project Aurora | Tax & Legal | Tomas Varga | Zurich | 2026-02-19 | 2026-04-10 | Delivered | 840 | 995 | 177.2 | 129.4 | 128.1 | 27.71% | -1.005% | 18.45% | 96.27% | Delivered ahead of plan; reference call agreed.
CE-2026-1040 | Project Pulsar | Consulting | Elena Popescu | Bratislava | 2026-02-20 | 2026-04-12 | On hold | 880 | 871 | 138.4 | 102.4 | 102.4 | 26.01% | 0% | -1.023% | 85.89% | Budget pressure from extra review cycles.
CE-2026-1041 | Project Quartz | Risk Advisory | Jakub Nowak | Bucharest | 2026-02-21 | 2026-04-14 | On track | 920 | 1191 | 146.4 | 109.8 | 159.2 | -8.743% | 44.99% | 29.46% | 66.44% | Key milestone met; partner readout next week.
CE-2026-1042 | Project Cobalt | Financial Advisory | Klara Schmidt | Budapest | 2026-02-22 | 2026-04-16 | At risk | 960 | 1056 | 154.5 | 117.4 | 119.7 | 22.52% | 1.959% | 10% | 79.08% | Dependency on client IT release.
CE-2026-1043 | Project Delta | Audit & Assurance | Andrei Ionescu | Warsaw | 2026-02-23 | 2026-04-18 | On track | 1000 | 905 | 162.8 | 125.4 | 129.2 | 20.64% | 3.03% | -9.5% | 97.24% | Scope stable; on plan.
CE-2026-1044 | Project Falcon | Tax & Legal | Maja Kovacevic | Ljubljana | 2026-02-24 | 2026-04-20 | Delivered | 1040 | 1258 | 171.2 | 106.1 | 110.3 | 35.57% | 3.959% | 20.96% | 73.56%
CE-2026-1045 | Project Granite | Consulting | Filip Urban | Zagreb | 2026-02-25 | 2026-04-22 | On track | 1080 | 1096 | 179.8 | 113.3 | 119 | 33.82% | 5.031% | 1.481% | 88.68% | Escalated to lead partner.
CE-2026-1046 | Project Harbor | Risk Advisory | Anna Kovac | Vienna | 2026-02-26 | 2026-04-24 | At risk | 1120 | 1478 | 188.6 | 120.7 | 127.9 | 32.18% | 5.965% | 31.96% | 68.98% | Client raised scope concerns on workstream 2.
CE-2026-1047 | Project Indigo | Financial Advisory | Marek Dvorak | Prague | 2026-02-27 | 2026-04-26 | Delivered | 1160 | 1305 | 197.4 | 128.3 | 137.3 | 30.45% | 7.015% | 12.5% | 81.76% | Awaiting client data; timeline slipping.
CE-2026-1048 | Project Juniper | Audit & Assurance | Petra Novak | Zurich | 2026-02-28 | 2026-04-28 | On hold | 1200 | 1116 | 206.5 | 136.3 | 147.2 | 28.72% | 7.997% | -7% | 100% | Strong client feedback at steering committee.
CE-2026-1049 | Project Kestrel | Tax & Legal | Lukas Weber | Bratislava | 2026-03-01 | 2026-04-30 | On track | 1240 | 1531 | 215.6 | 144.5 | 157.5 | 26.95% | 8.997% | 23.47% | 76.12% | Resourcing gap flagged for next month.
CE-2026-1050 | Project Larch | Consulting | Sofia Horvath | Bucharest | 2026-03-02 | 2026-05-02 | At risk | 1280 | 1331 | 225 | 153 | 168.3 | 25.2% | 10% | 3.984% | 91.38% | Change request pending approval.
CE-2026-1051 | Project Maple | Risk Advisory | Tomas Varga | Budapest | 2026-03-03 | 2026-05-04 | On Track | 1320 | 1775 | 234.4 | 161.7 | 179.5 | 23.42% | 11.01% | 34.47% | 71.38% | Delivered ahead of plan; reference call agreed.
CE-2026-1052 | Project Atlas | Financial Advisory | Elena Popescu | Warsaw | 2026-03-04 | 2026-05-06 | Delivered | 1360 | 1563 | 244.1 | 170.9 | 191.4 | 21.59% | 12% | 14.93% | 84.42% | Budget pressure from extra review cycles.
CE-2026-1053 | Project Helix | Audit & Assurance | Jakub Nowak | Ljubljana | 2026-03-05 | 2026-05-08 | On track | 1400 | 1337 | 253.8 | 180.2 | 203.6 | 19.78% | 12.99% | -4.5% | 102.6% | Key milestone met; partner readout next week.
CE-2026-1054 | Project Meridian | Tax & Legal | Klara Schmidt | Zagreb | 2026-03-06 | 2026-05-10 | At risk | 1440 | 1814 | 263.7 | 189.9 | 216.5 | 17.9% | 14.01% | 25.97% | 78.58% | Dependency on client IT release.
CE-2026-1055 | Project Vega | Consulting | Andrei Ionescu | Vienna | 2026-03-07 | 2026-05-12 | Delivered | 1480 | 1576 | 273.8 | 199.9 | 229.9 | 16.03% | 15.01% | 6.486% | 93.91% | Scope stable; on plan.
CE-2026-1056 | Project Orion | Risk Advisory | Maja Kovacevic | Prague | 2026-03-08 | 2026-05-14 | On hold | 1520 | 2082 | 284 | 210.2 | 243.8 | 14.15% | 15.98% | 36.97% | 73.73%
CE-2026-1057 | Project Lyra | Financial Advisory | Filip Urban | Zurich | 2026-03-09 | 2026-05-16 | On track | 1560 | 1833 | 294.4 | 220.8 | 258.3 | 12.26% | 16.98% | 17.5% | 86.82% | Escalated to lead partner.
CE-2026-1058 | Project Nova | Audit & Assurance | Anna Kovac | Bratislava | 2026-03-10 | 2026-05-18 | At risk | 1600 | 1568 | 304.9 | 231.7 | 273.4 | 10.33% | 18% | -2% | 105.1% | Client raised scope concerns on workstream 2.
CE-2026-1059 | Project Aurora | Tax & Legal | Marek Dvorak | Bucharest | 2026-03-11 | 2026-05-20 | On track | 1640 | 2107 | 315.5 | 242.9 | 289.1 | 8.368% | 19.02% | 28.48% | 80.94% | Awaiting client data; timeline slipping.
CE-2026-1060 | Project Pulsar | Consulting | Petra Novak | Budapest | 2026-03-12 | 2026-05-22 | Delivered | 1680 | 1831 | 326.3 | 202.3 | 242.8 | 25.59% | 20.02% | 8.988% | 96.33% | Strong client feedback at steering committee.
CE-2026-1061 | Project Quartz | Risk Advisory | Lukas Weber | Warsaw | 2026-03-13 | 2026-05-24 | On track | 1720 | 2399 | 337.3 | 212.5 | 257.1 | 23.78% | 20.99% | 39.48% | 76% | Resourcing gap flagged for next month.
CE-2026-1062 | Project Cobalt | Financial Advisory | Sofia Horvath | Ljubljana | 2026-03-14 | 2026-05-26 | At risk | 1760 | 2112 | 348.4 | 223 | 272.1 | 21.9% | 22.02% | 20% | 89.17% | Change request pending approval.
CE-2026-1063 | Project Delta | Audit & Assurance | Tomas Varga | Zagreb | 2026-03-15 | 2026-05-28 | Delivered | 1800 | 1809 | 359.6 | 233.7 | 287.5 | 20.05% | 23.02% | 0.5% | 107.5% | Delivered ahead of plan; reference call agreed.
CE-2026-1064 | Project Falcon | Tax & Legal | Elena Popescu | Vienna | 2026-03-16 | 2026-05-30 | On hold | 1840 | 2410 | 371 | 244.9 | 303.7 | 18.14% | 24.01% | 30.98% | 83.21% | Budget pressure from extra review cycles.