Central Europe Advisory — Monthly Leadership Review

Date:  Thursday 18 June 2026, 10:00–10:45 CEST

Type:  Microsoft Teams meeting (transcribed) — fictional demo content

Attendees:  Anna Kovac (Consulting), Marek Dvorak (Risk Advisory), Petra Novak (Financial Advisory), Tomas Varga (Tax & Legal), Sofia Horvath (Audit & Assurance)

Transcript

Anna Kovac:  Thanks everyone. Let's keep this to forty-five minutes. Agenda: portfolio health, three at-risk engagements, resourcing for Q3, and the Atlas decision. Petra, can you start with the numbers?

Petra Novak:  Sure. Quarter to date, fees are tracking slightly ahead of plan, but margin is down about two points, mostly from extra review cycles on a few engagements. Realisation is healthy except on Helix and Pulsar.

Marek Dvorak:  Helix is the invoice dispute — forty-eight thousand euros on two change requests. We think we have email approval but not signed. Priya is confirming today.

Anna Kovac:  Decision: we hold firm on the change requests if we can show written approval, otherwise we negotiate. Marek, you own getting that confirmed by Friday.

Tomas Varga:  On Meridian, the partner readout is Friday. Status is green, but the client hinted at a follow-on tax piece. We should be ready to scope it.

Sofia Horvath:  Audit side is stable. My concern is resourcing — I have two seniors finishing in July and three engagements ramping. If we don't confirm secondees we'll slip.

Anna Kovac:  Agreed. Action: each of us confirms secondee availability for Q3 to Talent by Friday. Sofia, flag the two roles you most need filled.

Petra Novak:  On Atlas — the steering committee approved the change request and the revised timeline. They confirmed the two SMEs for July. Go-live still depends on the client's IT release on the tenth.

Marek Dvorak:  So the main open risk on Atlas is the IT dependency. I'll add it to the risk log and we track it weekly.

Anna Kovac:  Good. Last item — margin. Decision: from next week, any engagement with budget variance over ten percent gets a partner review before the next invoice. Petra will pull the list.

Tomas Varga:  Makes sense. I'll bring the Tax pipeline numbers to the next review.

Anna Kovac:  Thanks all. To recap the decisions: hold on Helix pending written approval, confirm Q3 secondees by Friday, partner review for any variance over ten percent, and weekly tracking of the Atlas IT dependency. Let's close there.